## Sheet1
Project cost | Resource | Resource Rate (per week) | Duration (Weeks) | Resource Cost | Task Cost | Total
1. Hardware | [5 empty] | nil
2. Analysis | [5 empty] | 47.727
2.1 Feasibility research | BSA | 7.955 | 2 | 15.909 | 15.909
2.2 Requirements gathering and specifications | BSA | 7.955 | 4 | 31.818 | 31.818
3. Design & development | [5 empty] | 147.5
3.1 Development | BSA | 7.955 | 6 | 47.727
| developer | 6.818 |  | 40.909
| designer | 6.818 |  | 40.909 | 129.545
3.2 CRM specialist | specialist | 10000 | 1 | 10 | 10
3.3 Training and user guide documentation | BSA | 7.955 | 1 | 7.955 | 7.955
4. Testing & implementation | [5 empty] | 115.909
4.1 Testing | BSA | 7.955 | 2 | 15.909
| developer | 6.818 |  | 13.636
| designer | 6.818 |  | 13.636 | 43.182
4.2 Bug fixes, re-work from testing | developer | 6.818 | 2 | 13.636
| designer | 6.818 |  | 13.636 | 27.273
4.3 Post-go-live support | BSA | 7.955 | 4 | 31.818
| developer (50%) | 3.409 |  | 13.636 | 45.455
5. Project management | Vuyelwa | 5.114 | 18 | 92.045 |  | 92.095
Total | [5 empty] | 403.182